## Material
| Price | Count | Total | Comments
Scintillators |  | 259 | 92000 | 6 weeks lead time, Saint Gobain BC408 (quote from 12/20/13 below)
Light guides |  |  | - | included in scintillators
Wrapping |  |  | - | included in scintillators
MPPT | 23 | 538 | 12374 | 2*244+spares, Hamamatsu S12572-025P, 6-8 weeks lead time
Driver board | 72 | 288 | 20736 | 244+spares, lead time?
Cables |  |  | 8000 | see below
Lead sheet |  |  | 8000
Holding structure |  |  | 20000
Slow control |  |  | 5200
Total |  |  | 166310
Important: Realise it is asumed the ANDY Qtboards and so on can be used.
Scintillators (size x,y,z in cm) |  | count+spare
A (80.9, 4.0, 1.0) |  | 50+3 |  | narrow short (near beam pipe top and side)
B (100.2, 4.0, 1.0) |  | 56+3 |  | narrow long
C (66.3, 4.0, 1.0) |  | 6+1 |  | narrow very short (near beam pipe bottom)
D (85.6, 4.0, 1.0) |  | 14+1 |  | narrow mid1 (layer1 bottom)
E (92.2, 4.0, 1.0) |  | 14+1 |  | narrow mid2 (layer2 bottom)
F (100.2, 5.8 ,1.0) |  | 70+4 |  | wide long
G (85.6, 5.8, 1.0) |  | 18+1 |  | wide short1 (layer1 bottom)
H (92.2, 5.8, 1.0) |  | 16+1 |  | wide short2 (layer2 bottom)
Sum |  | 244+15
Cables
RG-58 | 0.15 | 10240 | 1536 | 40 ft per channel at $0.15/ft
Positronix contacts | 3.21 | 256 | 821.76
lemo connectors | 11.5 | 256 | 2944
Positronix shells | 1.94 | 32 | 62.08 | 8 channels each
Labor to bundle | 74 | 32 | 2368
LV & FEE cables |  |  | 1000 | estimate
Total |  |  | 7731.84

## Details FEE
Cost estimates (materials & vendor services) for FMS PS version of SiPM FEE board
This is 2-SiPM summed, 2 ch temp compensated voltage regulator, board about 35 x 70 mm
G. Visser, IU
2013-11-05
Assembly qty | 300 | (3*4*21 + spares)
Total cost | 22151.3189
Item | Qty/bd | Assy Excess | Qty needed | Mult | Qty buy | Cost ea. | Line cost | BOE/notes
signal conn (EPK.00.250.NTN) | 1 | 1 | 300 | 1 | 300 | 12.37 | 3711 | online pricing (Digikey)
pwr/control conn (N3314-5202RB) | 1 | 1 | 300 | 1 | 300 | 1.691 | 507.3 | online pricing (Digikey)
DAC (AD5622) | 3 | 1.05 | 945 | 1 | 945 | 1.6718 | 1579.8888 | online pricing (Digikey)
voltage reference (ADR433ARMZ) | 1 | 1.05 | 315 | 1 | 315 | 4.2381 | 1335.0078 | online pricing (Digikey)
DS2413 | 1 | 1.05 | 315 | 1 | 315 | 1.235 | 389.025 | online pricing (Digikey)
regulator opamp (LTC6081) | 1 | 1.05 | 315 | 1 | 315 | 2.18 | 686.7 | online pricing (Digikey)
regulator feedback R | 2 | 1.05 | 630 | 1000 | 1000 | 0.04 | 40 | online pricing (Digikey)
regulator transistors | 4 | 1.05 | 1260 | 1 | 1260 | 0.16 | 201.6 | aggregate estimate
bias bypass cap | 2 | 1.05 | 630 | 1 | 630 | 0.356 | 224.28 | online pricing (Digikey)
5V regulator (LT1761) | 1 | 1.05 | 315 | 1 | 315 | 1.9221 | 605.4615 | online pricing (Digikey)
tantalum cap (TPSB476K010R0250) | 2 | 1.05 | 630 | 1 | 630 | 0.50626 | 318.9438 | online pricing (Digikey)
preamp transistor (BFR92AW) | 2 | 1.05 | 630 | 1 | 630 | 0.1729 | 108.927 | online pricing (Digikey)
preamp opamp (OPA836) | 3 | 1.05 | 945 | 250 | 1000 | 1.2521 | 1252.12 | online pricing (Digikey)
various R | 48 | 1.1 | 15840 | 1 | 15840 | 0.025 | 396 | aggregate estimate
various C | 17 | 1.1 | 5610 | 1 | 5610 | 0.0665 | 373.065 | aggregate estimate
printed circuit board | 1 | 1 | 300 | 1 | 300 | 11.74 | 3522 | online quote (Sierra Circuits)
contract assembly | 1 | 1 | 300 | 1 | 300 | 23 | 6900 | online rough estimate (Sierra)

## Schedule
| Milestone | Tasks | Additional tasks
2014-12-20 | Installation complete
Installation (A,O,OP)
Full test with cosmics (O,A)
2014-10-15 | All quadrants assembled
|  | Assembly of remaining quadrants(O,A,OP) | Online monitoring and slow control (O,A)
Test with cosmics (O,A)
2014-08-31 | First quadrants assembled
|  | Assembly of first quadrant (A,O,OP,summer-student) | First full simulation in starsim (O)
Establish assembly technique (A,O,OP)
2014-07-31 | All items at BNL
|  | Characterization of all MPPTs (E,O,A,summer-student) | Start development of analysis procedure & database(O,A)
|  | Radation test of single channel in situ (O,A) | Finish the FMS offline reconstruction
|  | Construction of support structure(OP) | Include preshower in starsim in official CVS (A)
Initial test of single channel (O,A)
2014-05-31 | FEE board goes to production
2014-03-15 | Orders for all compoments out | - scintillator/light guide/wrapping - 6weeks (A)
- Hamamatsu S12572-025P - 6 weeks (E)
- support material & lead (OP)
- Cables (O,A)
- slow control (O,A)
2/29/14 | Final design
Finalize detector layout(E,O,A,J)
|  | Finalize support structure layout (OP) | Finish fast simulation for granularity (O)
FEE board design(G)
2014-02-15 | Light yield measurement
|  | Light yeild and uniformity measurements(O,A) | Finish optical simulation (O)
mini DAQ system for test (A)
Order Schintillators and SiPM for tests (E,A)
E=Elke,O=Oleg,A=Akio,OP(STAR-OP/John),G=Gerard